| January | Corporate | Street Academy 300 street kids, Accra Ghana (800 children attend events) | Springside Academy 350 Children 50 of them Orphans Kitale Kenya | Zorko Tadongo Village Approx. 200 children, 27 families | Naidvar Trust Music Academy | Tarongo School 2000 Children | St Theresa Health/ Hospital Zorko Outpatients, Maternity, 7 inpatient beds, Mental Health | Naidvar Brazil Barca Literaria |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | - Filed IRS Tax Return - Annual accounts complete for 2024. - Paid Incorporation fee, and re registered company. - Annual Report being drafted - Orientation of new Volunteers Aishath complete - Evaluation of Board 2024 - 1st face to face team meeting took place 9th Jan - 16 Jan Orientation complete AR - DL AND DKibbe had meeting 21 Jan 2025 to discuss website | - Breakfast funded - Nutrition project funded - ENT specialist will come and test the hearing of 70 children. A project set up by Aishath Rahila. Fundraising has begun. | - Proposal from Aishath to undertake Audiology tests in August - 3. Ex students funded for university - Funded all fertilizer costs | - Supporting craft center build - Commenced registration of all children including health insurance. | - Scoping exercise to assess issues of child trafficking. | - Information being collected on the priorities for 2025. This will go to JC for ideas on fundraising. - Four classrooms with children sitting on the floor. Costing desks for 1 classroom. | - Supporting health insurance cover for local children - 9 Jan meeting to set plan to register children to reduce trafficking - Registration to be one village at a time, starting 18th Jan | - Update from PN at team meeting - Meeting with Barca 19th Jan |

| February | Corporate | Street Academy 200+ street kids, Accra Ghana | Springside Academy 350 Children 50 of them Orphans Kitale Kenya | Zorko Tadongo Village Approx. 200 children, 27 families | Naidvar Trust Music Academy | Tarongo School 844 Children | St Theresa Health/ Hospital Zorko Outpatients, Maternity, 7 inpatient beds, Mental Health | Naidvar Brazil Barca Literaria |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | - Paid Registered Agent - Paid Corporate filing - Website being reviewed and possible renew. - Meetings to discuss Elsevier producing children’s books on sustainability. - Group WhatsApp set up with TS, AR and Elsevier to share ideas - Board meeting 9th Feb | - Breakfast funded - Nutrition project continues - Teacher training for 2 days - Totally reviewing diet plans- concerns they are not following the plans - 8o children health insurance renewed | - Fertilizer and farming goods funded - Medical costs covered for Eliud’s child. - Death of Sheril due to sickle cell disease brings the reality of children in poverty. | - Recycling training for full village - Basket weavers Loan reviewed awaiting report. - Craft center meeting to discuss next phase. It was agreed to start getting doors and windows to stop wildlife from moving in. - Basket weavers report complete. 22/7 Total loans 7,000 cedi 60 women | - Slows Leg healed after 4 years of non-Union. - Preparing to move to Zorko | - Funded school wiring to get hooked onto electric, to start computer training. | - Health Insurance paid for 100 children | Gisele had a bad case of Covid-19 and needed admission to hospital. Communications will resume once she has recovered. |

| March | Corporate | Street Academy 300 street kids, Accra Ghana (800 children attend events) | Springside Academy 350 Children 50 of them Orphans Kitale Kenya | Zorko Tadongo Village Approx. 200 children, 27 families | Tarongo School 844 Children | St Theresa Health/ Hospital Zorko Outpatients, Maternity, 7 inpatient beds, Mental Health | Naidvar Brazil Barca Literaria |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | - Group Meeting with Elsevier agreed to progress with Children’s books on sustainability - Brought Naidvartrust.com - Final draft Annual report circulated to Board 13th March - Annual Report 2024 circulated 29th March 2025 - DK and Lucky working on new website - 1st draft of book on Plant a tree complete, approved by Zorko school | - Breakfast Paid - Nutrition Project paid - Marwa communication with Felicia regarding exact information on nutrition - Eid Party supported | - Spring crop funded | - Basket weavers loan moving into savings scheme - Health insurance paid - Lillian Computer training extended - Malaria – Treatment provided ( Education given) | - Needs Assessment updated - Table and chairs funded - Commenced art project for Naidvar Book on Sustainability | - Donated to children’s health insurance and registration - Needs Assessment updated - Donation for roof repairs | - Awaiting Engineers expert report on the stability of the main house structure. - PN asked for update of priority needs for 2025 - Long term activities plan in discussion |

| April | Corporate | Street Academy 300 street kids, Accra Ghana (800 children attend events) | Springside Academy 350 Children 50 of them Orphans Kitale Kenya | Zorko Tadongo Village Approx. 200 children, 27 families | Tarongo School 2000 Children | St Theresa Health/ Hospital Zorko Outpatients, Maternity, 7 inpatient beds, Mental Health | Naidvar Brazil Barca Literaria |
| --- | --- | --- | --- | --- | --- | --- | --- |
| May | Corporate | Street Academy 300 street kids, Accra Ghana (800 children attend events) | Springside Academy 350 Children 50 of them Orphans Kitale Kenya | Zorko Tadongo Village Ghana Approx. 200 children, 27 families | Tarongo School 450+ Children Ghana | St Theresa Hospital Zorko Ghana | Naidvar Brazil Barca Literaria |
| June | Corporate | Street Academy 300 street kids, Accra Ghana (800 children attend events) | Springside Academy 350 Children 50 of them Orphans Kitale Kenya | Zorko Tadongo Village Ghana Approx. 200 children, 27 families | Tarongo School 450+ Children Ghana | St Theresa Hospital Zorko Ghana | Naidvar Brazil Barca Literia |
| July | Corporate | Street Academy 300 street kids, Accra Ghana (800 children attend events) | Springside Academy 350 Children 50 of them Orphans Kitale Kenya | Zorko Village Ghana Approx. 200 children, 27 families | Zorko School 450+ Children Ghana | Hospital Zorko Ghana | Barca Literaria |
| Aug | Corporate | Street Academy 300 street kids, Accra Ghana (800 children attend events) | Springside Academy 350 Children 50 of them Orphans Kitale Kenya | Zorko Village Ghana Approx. 200 children, 27 families | Zorko School 450+ Children Ghana | Hospital Zorko Ghana | Barca Literaria |
| Sep | Corporate | Street Academy 300 street kids, Accra Ghana (800 children attend events) | Springside Academy 350 Children - f them Orphans Kitale Kenya | Zorko Village Ghana Approx. 200 children, 27 families | Zorko School 2000 Children Ghana | Hospital Zorko Ghana | Barca Literaria Brazil |
| Oct | Corporate | Street Academy 300 street kids, Accra Ghana (800 children attend events) | Springside Academy 350 Children 50 of them Orphans Kitale Kenya | Zorko Village Ghana Approx. 200 children, 27 families | Zorko School 450+ Children Ghana | Hospital Zorko Ghana | Barca Literaria |
| Nov | Corporate | Street Academy 300 street kids, Accra Ghana (800 children attend events) | Springside Academy 350 Children 50 of them Orphans Kitale Kenya | Zorko Village Ghana Approx. 200 children, 27 families | Zorko School 2000 Children Ghana | Hospital Zorko Ghana | Barca Literaria |
| Dec | Corporate | Street Academy 300 street kids, Accra Ghana (800 children attend events) | Springside Academy 350 Children 50 of them Orphans Kitale Kenya | Zorko Village Ghana Approx. 200 children, 27 families | Zorko School 2000 Children Ghana | Hospital Zorko Ghana | Barca Literaria |